## Sheet1
DOOR HARDWARE
| Category | Item Description | Model No. | Quantity | Location | Vendor (KCC Suggestion) | Ordered by | Status (On-site, Available, Backordered) | Projected Delivery Date | Notes/Website
| Deadbolt System |  |  | 3 | Front Door and Garage Entries
| Door Hardware |  |  | 13 | All new door locations
| Lock Set |  |  | 6
| Door Stop |  |  | 12
| Bi-Closet Hardware |  |  | 2 | Bedroom 1 and 2
| 2-Door |  |  | 1 | Master Bedroom
| Pocket Door Hardware |  |  | 4 | Hall Bath 2, Bath 1, Pantry, Master
| Garage Door |  |  | 1 | Garage
| Single Swing Doors |  |  | 13
| Deadbolt Doors |  |  | 3 | [5 empty] | Red circles 1, 2, and 3
| Double Swing Doors |  |  | 3 | [5 empty] | (2) Double Swing Doors are closets
| Pocket Doors |  |  | 4
PLUMBING FIXTURES
| Category | Item Description | Model No. | Quantity | Location | Vendor (KCC Suggestion) | Ordered by | Status (On-site, Available, Backordered) | Projected Delivery Date | Notes/Website
| Toilet |  |  | 4 | All Bathrooms | (Belmont Hardware)
| Kitchen Sink |  |  | 1 | Kitchen
| Sink |  |  | 2 | Master Bathroom | (Belmont Hardware)
| Sink |  |  | 1 | Bath 1 | (Belmont Hardware)
| Sink | Desc |  | 1 | Hall Bath 1 | (Belmont Hardware)
| Sink |  |  | 1 | Hall Bath 2 | (Belmont Hardware)
| Faucet |  |  | 5 | All Bathrooms | (Belmont Hardware)
| Shower Trim |  |  |  | All Bathrooms w/ Showers | (Belmont Hardware)
| Shower Valve |  |  |  | All Bathrooms w/ Showers | (Belmont Hardware)
| Showerhead |  |  | 3 | Hall Bath 2 | (Belmont Hardware)
| Drain |  |  | 2 | Master Bathroom and Bath 1 | (Belmont Hardware) |  |  |  | Drain roughs material must be cast iron
| Tub Drain/Overflow Drain |  |  | 1 | Hall Bath 2
| Water Heater System | [8 empty] | Optional.
| Water Filtration System | [8 empty] | Optional.
| Garbage Disposal |  |  | 1 | Kitchen
| Tub |  |  | 1 | Hall Bath 2 | (Belmont Hardware)
| Washer-Dryer System |  |  | 1 pair | Garage |  |  |  |  | Reusing?
| Fireplace |  |  | 1 | Living Room
SURFACE MOUNTED LIGHT FIXTURES
| Category | Item Description | Model No. | Quantity | Location | Vendor (KCC Suggestion) | Ordered by | Status (On-site, Available, Backordered) | Projected Delivery Date | Notes/Website
| Chandelier |  |  | 1 | [5 empty] | Optional.
| Pendant |  |  | 3 | Over Kitchen Island |  |  |  |  | Optional.
| LED "Shop" Light |  |  |  | Garage |  |  |  |  | Optional.
| Strip Light |  |  |  | Closets in Bedroom 1, 2, and 3 |  |  |  |  | For closet lighting. Can be automated.
| Sconces |  |  |  | Master and Bedrooms 1, 2, and 3 |  |  |  |  | On headboard wall? Optional.
| Decorative Lighting (Misc.) |  |  |  | Front Door lighting |  |  |  |  | Optional.
| Sun Tunnel |  |  | 2 | Hall | (Bruce Bauer)
| Exterior Light Fixtures |  |  | 6
| Exterior Flood Lights |  |  | 3
CABINET HARDWARE
| Category | Item Description | Model No. | Quantity | Location | Vendor (KCC Suggestion) | Ordered by | Status (On-site, Available, Backordered) | Projected Delivery Date | Notes/Website
| Cabinetry | Pre Fab |  |  | Kitchen
|  | Pre Fab |  |  | Bathroom Vanities
Pre Fab
BATH ACCESSORIES
| Category | Item Description | Model No. | Quantity | Location | Vendor (KCC Suggestion) | Ordered by | Status (On-site, Available, Backordered) | Projected Delivery Date | Notes/Website
| Towel Warmer |  |  |  | Master Bathroom |  |  |  |  | Optional.
| Towel Warmer |  |  |  | Bath 1 |  |  |  |  | Optional.
| Towel Bar |  |  |  | Hall Bath 2
| Towel Bar |  |  |  | Bath 1
| Towel Bar |  |  |  | Master Bathroom
| Robe Hook |  |  |  | Bath 1
| Robe Hook |  |  |  | Master Bathroom
| Toilet Paper Holder |  |  | 4 | All Bathrooms
| Medicine Cabinet |  |  | 2 | Master Bathroom |  |  |  |  | Wall-mounted?/Recessed?
| Medicine Cabinet |  |  | 1 | Bath 1 |  |  |  |  | Wall-mounted?/Recessed?
| Medicine Cabinet |  |  | 1 | Hall Bath 2 |  |  |  |  | Wall-mounted?/Recessed?
| Medicine Cabinet |  |  | 1 | Hall Bath 1 |  |  |  |  | Wall-mounted?/Recessed?
Heating Pad/Heated Floor
TILES AND COUNTERTOPS
**Tile Locations Needed** | Category | Item Description | Model No. | Quantity | Location | Vendor (KCC Suggestion) | Ordered by | Status (On-site, Available, Backordered) | Projected Delivery Date | Notes/Website
| Tile Material |  |  |  | All Bathrooms | (Carmel Stone/DaVinci Marble) |  |  |  | Wainscots?
| Kitchen Backsplash |  |  |  | Kitchen | (Carmel Stone/DaVinci Marble) |  |  |  | Full/Partial?
| Kitchen Island | [8 empty] | Miter edge or Waterfall design?
|  | Glossy Field 3x6" | Neri White | 1 |  | All Natural Stone |  |  |  | Yolanda Jaimes <408.544.9600>
| Countertop Material | Statuario Venato Quartz Slab | VENATO | 3 | All Bathrooms and Kitchen Island | All Natural Stone |  |  |  | Yolanda Jaimes <408.544.9600>
HARDWOOD FLOOR
**Hardwood Floor Locations Needed** | Category | Item Description | Model No. | Quantity | Location | Vendor (KCC Suggestion) | Ordered by | Status (On-site, Available, Backordered) | Projected Delivery Date | Notes/Website
CARPET FLOOR
**Carpet Floor Locations Needed** | Category | Item Description | Model No. | Quantity | Location | Vendor (KCC Suggestion) | Ordered by | Status (On-site, Available, Backordered) | Projected Delivery Date | Notes/Website
KITCHEN APPLIANCES
| Category | Item Description | Model No. | Quantity | Location | Vendor (KCC Suggestion) | Ordered by | Status (On-site, Available, Backordered) | Projected Delivery Date | Notes/Website
| Hood Vent | Thermador Integrated Blower | VTN1090R | 1 | Kitchen
| Gas Range | 36" Thermador Smart Gas Range | PRG366WH | 1 | Kitchen
| Dishwasher | 24" Thermador Dishwasher | DWHD650WPR | 1 | Kitchen
| Refrigerator w/ Freezer | 36" Thermador Smart Ref. | T36IT905NP | 1 | Kitchen
| Microwave |  |  | 1 | Kitchen |  |  |  |  | Not shown in plans/Appliance order.
| Beverage Cooler | 24" Zephyr Beverage Cooler | PRB24C01BG | 1 | Kitchen
| Oven | 30" Thermador Speed Oven | MC30WP | 1 | Kitchen
WALLPAPER (if required)
**Wallpaper (if required) Locations Needed** | Category | Item Description | Model No. | Quantity | Location | Vendor (KCC Suggestion) | Ordered by | Status (On-site, Available, Backordered) | Projected Delivery Date | Notes/Website
PAINT COLORS
| Category | Item Description | Model No. | Quantity | Location | Vendor (KCC Suggestion) | Ordered by | Status (On-site, Available, Backordered) | Projected Delivery Date | Notes/Website
Ceiling
Wall
Siding (Exterior)
Cabinets
Doors